## Slide 1
Project Scheduling:
Network Diagrams

## Slide 2
PROJECT SCHEDULING
Scope Management
  Work Breakdown Structure
    Deliverables
      Work Packages
        Activities
Project scheduling requires us to follow some carefully laid-out steps, in order, for the schedule to take shape - to present linked activities with planned dates, durations, milestones, and resources.

## Slide 3
PROJECT SCHEDULING
Project planning as it relates to the scheduling process, has been defined by the PMBoK as:
The identification of the project objectives and the ordered activity necessary to complete the project including the identification of resource types and quantities required to carry out each activity or task.

## Slide 4
PROJECT SCHEDULING
Project scheduling techniques lie at the heart of project planning and subsequent monitoring and control
Project scheduling represents the conversion of project goals into an achievable methodology for their completion; a timetable and the network logic that relates project activities to each other in a coherent fashion
Project scheduling defines network logic for all activities: tasks that must either precede or follow other tasks from the beginning of the project to completion

## Slide 5
PROJECT SCHEDULING
Project scheduling can take a lot of time and effort, but when done well…
Clearly illustrates the interdependence of all tasks and work packages
Facilitates communication flow
Helps with master scheduling of organisational resources
Identified critical activities & distinguishes them from the less critical
Provides expectation for when the project will be completed & dates on which various project activities must start and end
Helps with coordination of activities that are dependent on each other

## Slide 6
EXAMPLE
Project = research project (paper and presentation)
What steps do we need to complete? What order do they need to be completed in?

## Slide 7
EXAMPLE
Project = research project (paper and presentation)
Identify the topic
Research the topic
Write the first draft of the paper
Edit and rewrite the paper
Prepare a class presentation
Complete the final draft of the paper
Complete the presentation
Hand in the paper and present the topic in class

## Slide 8
EXAMPLE
Identify the topic
Research the topic
Write the first draft of the paper
Edit and rewrite the paper
Prepare a class presentation
Complete the final draft of the paper
Complete the presentation
Hand in the paper and present the topic in class

## Slide 9
EXAMPLE
Identify the topic
Research the topic
Write the first draft of the paper
Edit and rewrite the paper
Prepare a class presentation
Complete the final draft of the paper
Complete the presentation
Hand in the paper and present the topic in class
Identify topic
Research topic
First draft
Edit & rewrite
Prepare presentation
Complete final draft
Complete presentation
Hand in paper & present

## Slide 10
EXAMPLE
Identify the topic
Research the topic
Write the first draft of the paper
Edit and rewrite the paper
Prepare a class presentation
Complete the final draft of the paper
Complete the presentation
Hand in the paper and present the topic in class
Identify topic
Research topic
First draft

## Slide 11
EXAMPLE
Identify the topic
Research the topic
Write the first draft of the paper
Edit and rewrite the paper
Prepare a class presentation
Complete the final draft of the paper
Complete the presentation
Hand in the paper and present the topic in class
Identify topic
Research topic
First draft
Edit & rewrite
Prepare presentation
Complete final draft
Complete presentation

## Slide 12
EXAMPLE
Identify the topic
Research the topic
Write the first draft of the paper
Edit and rewrite the paper
Prepare a class presentation
Complete the final draft of the paper
Complete the presentation
Hand in the paper and present the topic in class
Identify topic
Research topic
First draft
Edit & rewrite
Prepare presentation
Complete final draft
Complete presentation

## Slide 13
EXAMPLE
Identify the topic
Research the topic
Write the first draft of the paper
Edit and rewrite the paper
Prepare a class presentation
Complete the final draft of the paper
Complete the presentation
Hand in the paper and present the topic in class
Identify topic
Research topic
First draft
Edit & rewrite
Prepare presentation
Complete final draft
Complete presentation
Hand in paper & present

## Slide 14
EXAMPLE
Identify the topic
Research the topic
Write the first draft of the paper
Edit and rewrite the paper
Prepare a class presentation
Complete the final draft of the paper
Complete the presentation
Hand in the paper and present the topic in class
Identify topic
Research topic
First draft
Edit & rewrite
Prepare presentation
Complete final draft
Complete presentation
Hand in paper & present
When the nature of the work allows for more than one activity to be accomplished at the same time, these activities are called concurrent, and parallel project paths are constructed through the network.

## Slide 15
TERMINOLOGY
Project network – a visual flow diagram developed from the WBS
Activity – an element in the project that consumes time
Parallel activities – can take place at the same time
Serial activities – those that flow from one to the next, in sequence
Merge activity – has more than one activity immediately preceding it
Burst activity – has more than one activity immediately following it
Event – term used to represent a point in time when an activity starts or ends. It does not consume time
Path – a sequence of connected, dependent activities
Critical path – the path with the longest duration, which determines the shortest project length

## Slide 16
Identify topic
Research topic
First draft
Edit & rewrite
Prepare presentation
Complete final draft
Complete presentation
Hand in paper & present
Project Network
Notes: Here we see a project network [click], which is the whole visual of the project
And we have each of these rectangles or nodes as activities.
We have a burst activity [click], where more than one activity immediately follows, and a merga ctivity [click] where more than one activity immediately precedes. And we’ll need to be able to recognise these activities when we start including timing for scheduling in our networks, which we’ll do in our second video..
And again, as we saw in the first example of thise project [click] we have some serial activities here – those activities that simply follow one after the other.

## Slide 17
Identify topic
Research topic
First draft
Edit & rewrite
Prepare presentation
Complete final draft
Complete presentation
Hand in paper & present
Project Network
Activity
Notes: Here we see a project network [click], which is the whole visual of the project
And we have each of these rectangles or nodes as activities.
We have a burst activity [click], where more than one activity immediately follows, and a merga ctivity [click] where more than one activity immediately precedes. And we’ll need to be able to recognise these activities when we start including timing for scheduling in our networks, which we’ll do in our second video..
And again, as we saw in the first example of thise project [click] we have some serial activities here – those activities that simply follow one after the other.

## Slide 18
Identify topic
Research topic
First draft
Edit & rewrite
Prepare presentation
Complete final draft
Complete presentation
Hand in paper & present
Project Network
Activity
Burst Activity
Notes: Here we see a project network [click], which is the whole visual of the project
And we have each of these rectangles or nodes as activities.
We have a burst activity [click], where more than one activity immediately follows, and a merga ctivity [click] where more than one activity immediately precedes. And we’ll need to be able to recognise these activities when we start including timing for scheduling in our networks, which we’ll do in our second video..
And again, as we saw in the first example of thise project [click] we have some serial activities here – those activities that simply follow one after the other.

## Slide 19
Identify topic
Research topic
First draft
Edit & rewrite
Prepare presentation
Complete final draft
Complete presentation
Hand in paper & present
Project Network
Activity
Burst Activity
Merge Activity
Notes: Here we see a project network [click], which is the whole visual of the project
And we have each of these rectangles or nodes as activities.
We have a burst activity [click], where more than one activity immediately follows, and a merga ctivity [click] where more than one activity immediately precedes. And we’ll need to be able to recognise these activities when we start including timing for scheduling in our networks, which we’ll do in our second video..
And again, as we saw in the first example of thise project [click] we have some serial activities here – those activities that simply follow one after the other.

## Slide 20
Identify topic
Research topic
First draft
Edit & rewrite
Prepare presentation
Complete final draft
Complete presentation
Hand in paper & present
Project Network
Activity
Burst Activity
Merge Activity
Serial Activities
Notes: Here we see a project network [click], which is the whole visual of the project
And we have each of these rectangles or nodes as activities.
We have a burst activity [click], where more than one activity immediately follows, and a merga ctivity [click] where more than one activity immediately precedes. And we’ll need to be able to recognise these activities when we start including timing for scheduling in our networks, which we’ll do in our second video..
And again, as we saw in the first example of thise project [click] we have some serial activities here – those activities that simply follow one after the other.

## Slide 21
Identify topic
Research topic
First draft
Edit & rewrite
Prepare presentation
Complete final draft
Complete presentation
Hand in paper & present
Project Network
Notes: Here we see a project network [click], which is the whole visual of the project
And we have each of these rectangles or nodes as activities.
We have a burst activity [click], where more than one activity immediately follows, and a merga ctivity [click] where more than one activity immediately precedes. And we’ll need to be able to recognise these activities when we start including timing for scheduling in our networks, which we’ll do in our second video..
And again, as we saw in the first example of thise project [click] we have some serial activities here – those activities that simply follow one after the other.

## Slide 22
Identify topic
Research topic
First draft
Edit & rewrite
Prepare presentation
Complete final draft
Complete presentation
Hand in paper & present
Project Network
Parallel Activities
Notes: Here we see a project network [click], which is the whole visual of the project
And we have each of these rectangles or nodes as activities.
We have a burst activity [click], where more than one activity immediately follows, and a merga ctivity [click] where more than one activity immediately precedes. And we’ll need to be able to recognise these activities when we start including timing for scheduling in our networks, which we’ll do in our second video..
And again, as we saw in the first example of thise project [click] we have some serial activities here – those activities that simply follow one after the other.

## Slide 23
Identify topic
Research topic
First draft
Edit & rewrite
Prepare presentation
Complete final draft
Complete presentation
Hand in paper & present
Project Network
Parallel Activities
Path 1
Notes: Here we see a project network [click], which is the whole visual of the project
And we have each of these rectangles or nodes as activities.
We have a burst activity [click], where more than one activity immediately follows, and a merga ctivity [click] where more than one activity immediately precedes. And we’ll need to be able to recognise these activities when we start including timing for scheduling in our networks, which we’ll do in our second video..
And again, as we saw in the first example of thise project [click] we have some serial activities here – those activities that simply follow one after the other.

## Slide 24
Identify topic
Research topic
First draft
Edit & rewrite
Prepare presentation
Complete final draft
Complete presentation
Hand in paper & present
Project Network
Parallel Activities
Path 1
Path 2
Notes: Here we see a project network [click], which is the whole visual of the project
And we have each of these rectangles or nodes as activities.
We have a burst activity [click], where more than one activity immediately follows, and a merga ctivity [click] where more than one activity immediately precedes. And we’ll need to be able to recognise these activities when we start including timing for scheduling in our networks, which we’ll do in our second video..
And again, as we saw in the first example of thise project [click] we have some serial activities here – those activities that simply follow one after the other.

## Slide 25
Project Scheduling:
Activity on Node Network Diagrams

## Slide 26
NETWORK DIAGRAMS
Two common approaches: AOA and AON
Both use the arrow and the node as building blocks
Activities represented by letters
AOA – arrows depict the activities

## Slide 27
NETWORK DIAGRAMS
Two common approaches: AOA and AON
Both use the arrow and the node as building blocks
Activities represented by letters
AOA – arrows depict the activities
AON – nodes depict the activities

## Slide 28
ACTIVITY ON NODE
In practice, AON has come to dominate
Activities represented by nodes
Arrows are merely connection devices – simplified network labeling
Easy to read & comprehend, even for novice project managers
Primary drawback – as the project becomes more complex the sheer number of arrows or nodes can become “messy”

## Slide 29
ACTIVITY ON NODE -FUNDAMENTALS
Predecessors: Those activities that must be completed prior to initiation of a later activity in the network.
Successors: Activities that cannot be started until previous activities have been completed. These activities follow predecessor tasks.

## Slide 30
ACTIVITY ON NODE - FUNDAMENTALS
A
B
C
A is preceded by nothing
B is preceded by A
C is preceded by B

## Slide 31
ACTIVITY ON NODE - FUNDAMENTALS
X
Y
Z
Y and Z are preceded by X
Y and Z can start at the same time if you wish

## Slide 32
ACTIVITY ON NODE - FUNDAMENTALS
J
M
L
J, K, and L can all start at the same time if you wish
(J, K, and L do not need to occur simultaneously)
BUT
J, K, and L must ALL finish before M can start
K

## Slide 33
ACTIVITY ON NODE – NETWORK DIAGRAM RULES
Some determination of activity precedence ordering must be done prior to creating the network (i.e., logically linking, successor, etc.)
Flow: left to right
An activity cannot begin until all preceding connected activities have been completed
Arrows on networks indicate precedence and logical flow. Arrows can cross over each other (but not recommended)
Unique identifier needed for each activity
Looping (or recycling) through activities is not permitted
Good to start and end with a single node (but not required)

## Slide 34
ACTIVITY ON NODE – THE NODE
Early Start (ES)
Early Finish (EF)
Late Start (LS)
Late Finish (LF)
Float (or Slack)
Unique Identifier (ID)
Duration
Activity Description

## Slide 35
ACTIVITY ON NODE – THE NODE
Early start (ES): The earliest an activity can start. It is the largest early finish of all immediate predecessors.
Late start (LS): The latest an activity can start and not delay the following activity/activities.
Early finish (EF): The earliest an activity can finish if all its preceding activities are finished by their early finish times.
Late finish (LF): The latest an activity can finish and not delay the following activity/activities.
Activity float (slack): The amount of time an activity may be delayed from its early start without delaying the finish of the project.
Identifier: The unique identifier for the activity (can be a letter)

## Slide 36
AON – DRAWING THE DIAGRAM
Activity | Description | Predecessor
A | Contract signing | None
B | Questionnaire design | A
C | Target market ID | A
D | Survey sample | B, C
E | Develop presentation | B
F | Analyse results | D
G | Demographic analysis | C
H | Presentation to client | E, F, G

## Slide 37
AON – DRAWING THE DIAGRAM

## Slide 38
ACTIVITY DURATIONS
How might we figure out how long an activity could take?
Experience
Expert opinion
Mathematical derivation

## Slide 39
ACTIVITY DURATIONS
How might we figure out how long an activity could take?
Experience
Expert opinion
Mathematical derivation
TE = estimated time (duration) of the activity
a = most optimistic time to complete the activity
m = most likely time to complete the activity
b = most pessimistic time to complete the activity

## Slide 40
ACTIVITY DURATIONS
Activity | Description | Most optimistic (a) | Most likely (m) | Most pessimistic (b) | Activity Duration (TE)
A | Contract signing | 3 | 4 | 11 | 
B | Questionnaire design | 2 | 5 | 8 | 
C | Target market ID | 3 | 6 | 9 | 
D | Survey sample | 8 | 12 | 20 | 
E | Develop presentation | 3 | 5 | 12 | 
F | Analyse results | 2 | 4 | 7 | 
G | Demographic analysis | 6 | 9 | 14 | 
H | Presentation to client | 1 | 2 | 4 | 

## Slide 41
ACTIVITY DURATIONS
Activity | Description | Most optimistic (a) | Most likely (m) | Most pessimistic (b) | Activity Duration (TE)
A | Contract signing | 3 | 4 | 11 | 5
B | Questionnaire design | 2 | 5 | 8 | 5
C | Target market ID | 3 | 6 | 9 | 6
D | Survey sample | 8 | 12 | 20 | 12.7 (13)
E | Develop presentation | 3 | 5 | 12 | 5.8 (6)
F | Analyse results | 2 | 4 | 7 | 4.2 (4)
G | Demographic analysis | 6 | 9 | 14 | 9.3 (9)
H | Presentation to client | 1 | 2 | 4 | 2.2 (2)

## Slide 42
AON – DRAWING THE DIAGRAM
Activity | Description | Predecessor | Duration
A | Contract signing | None | 5
B | Questionnaire design | A | 5
C | Target market ID | A | 6
D | Survey sample | B, C | 13
E | Develop presentation | B | 6
F | Analyse results | D | 4
G | Demographic analysis | C | 9
H | Presentation to client | E, F, G | 2

## Slide 43
AON – DRAWING THE DIAGRAM
Activity | Predecessor | Duration
A | None | 5
B | A | 5
C | A | 6
D | B, C | 13
E | B | 6
F | D | 4
G | C | 9
H | E, F, G | 2

## Slide 44
AON – DRAWING THE DIAGRAM

## Slide 45
AON: DRAWING THE DIAGRAM
A
B
C
D
E
F
G
H

## Slide 46
AON: DRAWING THE DIAGRAM
A
B
C
D
E
F
G
H
 | A | 
 | 5 | 
 | B | 
 | 5 | 
 | C | 
 | 6 | 
 | D | 
 | 13 | 
 | E | 
 | 6 | 
 | F | 
 | 4 | 
 | G | 
 | 9 | 
 | H | 
 | 2 | 

## Slide 47
AON – FILLING IN THE ACTIVITY NODES
How soon can our activities start? (ES)
How soon can each activity end? (EF)
How soon can the project be finished? (TE)
How late can the activity start? (LS)
How late can the activity finish? (LF)
Which activities represent the critical path? (CP) [the longest path which, when delayed, will delay the project]
How long can each activity be delayed? (float)

## Slide 48
AON – FILLING IN THE ACTIVITY NODES
How soon can our activities start? (ES)
How soon can each activity end? (EF)
How soon can the project be finished? (TE)
How late can the activity start? (LS)
How late can the activity finish? (LF)
Which activities represent the critical path? (CP) [the longest path which, when delayed, will delay the project]
How long can each activity be delayed? (float)
Forward Pass
Backward Pass

## Slide 49
AON – FORWARD PASS RULES
Add all activity times along each path as we move through the network (ES + Dur = EF).
Carry the EF time to the activity nodes immediately succeeding the recently completed node. That EF becomes the ES of the next node, unless the succeeding node is a merge point.
At a merge point, the largest preceding EF becomes the ES for that node
When we complete the forward pass we can calculate all ES, EF, and project TE
Forward pass: Network calculations to determine earliest start & earliest finish for an activity through working forward through each activity in network.

## Slide 50
AON: FORWARD PASS
A
B
C
D
E
F
G
H
0 | A | 5
 | 5 | 
5 | B | 10
 | 5 | 
5 | C | 11
 | 6 | 
11 | D | 24
 | 13 | 
10 | E | 16
 | 6 | 
24 | F | 28
 | 4 | 
11 | G | 20
 | 9 | 
28 | H | 30
 | 2 | 

## Slide 51
AON – BACKWARD PASS RULES
Subtract activity times along each path as you move through the network (LF – Dur = LS).
Carry back the LS time to the activity nodes immediately preceding the successor node. That LS becomes the LF of the next node, unless the preceding node is a burst point.
In the case of a burst point, the smallest succeeding LS becomes the LF for that node.
When we complete the forward pass we can calculate all LS, LF, and float
Backward pass: Network calculations to determine late start/late finish for uncompleted tasks through working backward through each activity

## Slide 52
AON: BACKWARD PASS
A
B
C
D
E
F
G
H
0 | A | 5
0 | 5 | 5
5 | B | 10
6 | 5 | 11
5 | C | 11
5 | 6 | 11
11 | D | 24
11 | 13 | 24
10 | E | 16
22 | 6 | 28
24 | F | 28
24 | 4 | 28
11 | G | 20
19 | 9 | 28
28 | H | 30
28 | 2 | 30

## Slide 53
AON: FLOAT
A
B
C
D
E
F
G
H
0 | A | 5
0 |  | 
0 | 5 | 5
5 | B | 10
1 |  | 
6 | 5 | 11
5 | C | 11
0 |  | 
5 | 6 | 11
11 | D | 24
0 |  | 
11 | 13 | 24
10 | E | 16
12 |  | 
22 | 6 | 28
24 | F | 28
0 |  | 
24 | 4 | 28
11 | G | 20
8 |  | 
19 | 9 | 28
28 | H | 30
0 |  | 
28 | 2 | 30
LF – EF = Float
LS – ES = Float
Activity Float/Slack: The amount of time that a schedule activity can be delayed without delaying the early start date to any immediately following schedule activities.

## Slide 54
AON – CRITICAL PATH
Critical path: The path through project network with the longest duration.
Critical Path Method: A network analysis technique used to determine the amount of schedule flexibility on logical network paths in project schedule network and to determine minimum project duration

## Slide 55
AON: CRITICAL PATH
A
B
C
D
E
F
G
H
0 | A | 5
0 |  | 
0 | 5 | 5
5 | B | 10
1 |  | 
6 | 5 | 11
5 | C | 11
0 |  | 
5 | 6 | 11
11 | D | 24
0 |  | 
11 | 13 | 24
10 | E | 16
12 |  | 
22 | 6 | 28
24 | F | 28
0 |  | 
24 | 4 | 28
11 | G | 20
8 |  | 
19 | 9 | 28
28 | H | 30
0 |  | 
28 | 2 | 30
What are our different paths?
How long are they?
Which is our Critical Path?
A-B-E-H = 18 days

## Slide 56
AON: CRITICAL PATH
A
B
C
D
E
F
G
H
0 | A | 5
0 |  | 
0 | 5 | 5
5 | B | 10
1 |  | 
6 | 5 | 11
5 | C | 11
0 |  | 
5 | 6 | 11
11 | D | 24
0 |  | 
11 | 13 | 24
10 | E | 16
12 |  | 
22 | 6 | 28
24 | F | 28
0 |  | 
24 | 4 | 28
11 | G | 20
8 |  | 
19 | 9 | 28
28 | H | 30
0 |  | 
28 | 2 | 30
What are our different paths?
How long are they?
Which is our Critical Path?
A-B-E-H = 18 days
A-B-D-F-H = 29 days

## Slide 57
AON: CRITICAL PATH
A
B
C
D
E
F
G
H
0 | A | 5
0 |  | 
0 | 5 | 5
5 | B | 10
1 |  | 
6 | 5 | 11
5 | C | 11
0 |  | 
5 | 6 | 11
11 | D | 24
0 |  | 
11 | 13 | 24
10 | E | 16
12 |  | 
22 | 6 | 28
24 | F | 28
0 |  | 
24 | 4 | 28
11 | G | 20
8 |  | 
19 | 9 | 28
28 | H | 30
0 |  | 
28 | 2 | 30
What are our different paths?
How long are they?
Which is our Critical Path?
A-B-E-H = 18 days
A-B-D-F-H = 29 days
A-C-D-F-H = 30 days
Notes: Path A-C-D-F-H takes 30 days

## Slide 58
AON: CRITICAL PATH
A
B
C
D
E
F
G
H
0 | A | 5
0 |  | 
0 | 5 | 5
5 | B | 10
1 |  | 
6 | 5 | 11
5 | C | 11
0 |  | 
5 | 6 | 11
11 | D | 24
0 |  | 
11 | 13 | 24
10 | E | 16
12 |  | 
22 | 6 | 28
24 | F | 28
0 |  | 
24 | 4 | 28
11 | G | 20
8 |  | 
19 | 9 | 28
28 | H | 30
0 |  | 
28 | 2 | 30
What are our different paths?
How long are they?
Which is our Critical Path?
A-B-E-H = 18 days
A-B-D-F-H = 29 days
A-C-D-F-H = 30 days
A-C-G-H = 22 days

## Slide 59
AON: CRITICAL PATH
A
B
C
D
E
F
G
H
0 | A | 5
0 |  | 
0 | 5 | 5
5 | B | 10
1 |  | 
6 | 5 | 11
5 | C | 11
0 |  | 
5 | 6 | 11
11 | D | 24
0 |  | 
11 | 13 | 24
10 | E | 16
12 |  | 
22 | 6 | 28
24 | F | 28
0 |  | 
24 | 4 | 28
11 | G | 20
8 |  | 
19 | 9 | 28
28 | H | 30
0 |  | 
28 | 2 | 30
What are our different paths?
How long are they?
Which is our Critical Path?
A-B-E-H = 18 days
A-B-D-F-H = 29 days
A-C-D-F-H = 30 days
A-C-G-H = 22 days

## Slide 60
Project Scheduling:
Crashing the Project

## Slide 61
RECALL: PROJECT SCHEDULING
Represents the conversion of project goals into an achievable methodology for their completion; a timetable and the network logic that relates project activities to each other in a coherent fashion
Clearly illustrates the interdependence of all tasks and work packages
Helps with master scheduling of organizational resources
Identification of critical activities & distinguishes them from the less critical
Provides expectation for when the project will be completed & dates on which various project activities must start & end
Helps with coordination of activities that are dependent on each other

## Slide 62
REDUCING THE CRITICAL PATH
When might we want to accelerate a project’s finish time?
The initial schedule may be too aggressive – we may have scheduled the project with a series of activity durations so condensed that crashing the project is inevitable
Market needs change and the completion of the project is required earlier than anticipated
The project has slipped significantly behind schedule
The contractual situation provides more incentive to avoid schedule slippage (e.g., late delivery penalties)
The process of accelerating a project is referred to as crashing

## Slide 63
CRASHING THE PROJECT
The process of accelerating a project
Primary methods for crashing:
Improving existing resources’ productivity
Changing work methods
Compromise quality and/or reduce project scope
Institute fast-tracking
Work overtime
Increasing the quantity of resources

## Slide 64
CRASHING THE PROJECT
The process of accelerating a project
Primary methods for crashing:
Improving existing resources’ productivity
Changing work methods
Compromise quality and/or reduce project scope
Institute fast-tracking
Work overtime
Increasing the quantity of resources

## Slide 65
CRASHING THE PROJECT
The process of accelerating a project
Primary methods for crashing:
Improving existing resources’ productivity
Changing work methods
Compromise quality and/or reduce project scope
Institute fast-tracking
Work overtime
Increasing the quantity of resources

## Slide 66
CRASHING THE PROJECT
The process of accelerating a project
Primary methods for crashing:
Improving existing resources’ productivity
Changing work methods
Compromise quality and/or reduce project scope
Institute fast-tracking
Work overtime
Increasing the quantity of resources

## Slide 67
CRASHING THE PROJECT
The process of accelerating a project
Primary methods for crashing:
Improving existing resources’ productivity
Changing work methods
Compromise quality and/or reduce project scope
Institute fast-tracking
Work overtime
Increasing the quantity of resources

## Slide 68
CRASHING THE PROJECT
The process of accelerating a project
Primary methods for crashing:
Improving existing resources’ productivity
Changing work methods
Compromise quality and/or reduce project scope
Institute fast-tracking
Work overtime
Increasing the quantity of resources

## Slide 69
TIME/COST TRADE-OFF

## Slide 70
TIME/COST TRADE-OFF

## Slide 71
TIME/COST TRADE-OFF
Slope = crash cost – normal cost normal time - crash time
We can calculate various combinations of time/cost trade-offs for a project’s crash options by calculating the slope for each activity

## Slide 72
EXAMPLE
SUPPOSE:
NORMAL ACTIVITY DURATION = 8 WEEKS
NORMAL COST = $14,000
CRASHED ACTIVITY DURATION = 5 WEEKS
CRASHED COST = $23,000

## Slide 73
EXAMPLE 1
SUPPOSE:
NORMAL ACTIVITY DURATION = 8 WEEKS
NORMAL COST = $14,000
CRASHED ACTIVITY DURATION = 5 WEEKS
CRASHED COST = $23,000
Slope = crash cost – normal cost normal time - crash time

## Slide 74
EXAMPLE 1
SUPPOSE:
NORMAL ACTIVITY DURATION = 8 WEEKS
NORMAL COST = $14,000
CRASHED ACTIVITY DURATION = 5 WEEKS
CRASHED COST = $23,000
Slope = $23,000 – $14,000 8 weeks – 5 weeks
Slope = crash cost – normal cost normal time - crash time
Slope = $9,000/3weeks

## Slide 75
EXAMPLE 1
SUPPOSE:
NORMAL ACTIVITY DURATION = 8 WEEKS
NORMAL COST = $14,000
CRASHED ACTIVITY DURATION = 5 WEEKS
CRASHED COST = $23,000
Slope = $23,000 – $14,000 8 weeks – 5 weeks
Slope = crash cost – normal cost normal time - crash time
Slope = $9,000/3weeks
Slope = $3,000/week

## Slide 76
Crashing the Project - Examples

## Slide 77
EXAMPLE 2
Suppose we have a project with the following 8 activities and we want to accelerate our project by crashing.
What do we need to do?

## Slide 78
EXAMPLE 2
Suppose we have a project with the following 8 activities and we want to accelerate our project by crashing.
What do we need to do?

## Slide 79
EXAMPLE 2
Suppose we have a project with the following 8 activities and we want to accelerate our project by crashing.
What do we need to do?

## Slide 80
EXAMPLE 2
Suppose we have a project with the following 8 activities and we want to accelerate our project by crashing.
What do we need to do?

## Slide 81
EXAMPLE 2
Suppose we have a project with the following 8 activities and we want to accelerate our project by crashing.
What do we need to do?

## Slide 82
EXAMPLE 2
Suppose we have a project with the following 8 activities and we want to accelerate our project by crashing.
What do we need to do?

## Slide 83
EXAMPLE 2
Slope = crash cost – normal cost normal time - crash time
Which activities are optimal for crashing?
1) Calculate the crash cost of each activity (slope)
2) Decide which activities we should crash

## Slide 84
EXAMPLE 2
Slope = crash cost – normal cost normal time - crash time
Which activities are optimal for crashing?
1) Calculate the crash cost of each activity (slope)
2) Decide which activities we should crash

## Slide 85
EXAMPLE 2
A
B
E
H
 | A | 
 | 5 | 
 | B | 
 | 7 | 
 | C | 
 | 3 | 
 | E | 
 | 9 | 
 | F | 
 | 4 | 
 | D | 
 | 5 | 
 | G | 
 | 6 | 
 | H | 
 | 8 | 
What is the critical path?
How many days is it?

## Slide 86
EXAMPLE 2
A
B
E
H
 | A | 
 | 5 | 
 | B | 
 | 7 | 
 | C | 
 | 3 | 
 | E | 
 | 9 | 
 | F | 
 | 4 | 
 | D | 
 | 5 | 
 | G | 
 | 6 | 
 | H | 
 | 8 | 
What is the critical path?
How many days is it?
A – D – E – H
27 days

## Slide 87
EXAMPLE 2
A
B
E
H
 | A | 
 | 5 | 
 | B | 
 | 7 | 
 | C | 
 | 3 | 
 | E | 
 | 9 | 
 | F | 
 | 4 | 
 | D | 
 | 5 | 
 | G | 
 | 6 | 
 | H | 
 | 8 | 

## Slide 88
EXAMPLE 2
A
B
E
H
 | A | 
 | 4 | 
 | B | 
 | 7 | 
 | C | 
 | 3 | 
 | E | 
 | 9 | 
 | F | 
 | 4 | 
 | D | 
 | 5 | 
 | G | 
 | 6 | 
 | H | 
 | 8 | 

## Slide 89
EXAMPLE 2
A
B
E
H
 | A | 
 | 4 | 
 | B | 
 | 7 | 
 | C | 
 | 3 | 
 | E | 
 | 9 | 
 | F | 
 | 4 | 
 | D | 
 | 5 | 
 | G | 
 | 6 | 
 | H | 
 | 8 | 

## Slide 90
EXAMPLE 2
A
B
E
H
 | A | 
 | 3 | 
 | B | 
 | 7 | 
 | C | 
 | 3 | 
 | E | 
 | 9 | 
 | F | 
 | 4 | 
 | D | 
 | 5 | 
 | G | 
 | 6 | 
 | H | 
 | 8 | 

## Slide 91
EXAMPLE 2
A
B
E
H
 | A | 
 | 3 | 
 | B | 
 | 6 | 
 | C | 
 | 3 | 
 | E | 
 | 9 | 
 | F | 
 | 4 | 
 | D | 
 | 5 | 
 | G | 
 | 5 | 
 | H | 
 | 8 | 
A-B-F-H = 21
A-C-E-H = 21
A-D-E-H = 25
A-D-E-H = 21

## Slide 92
EXAMPLE 2
A
B
E
H
 | A | 
 | 3 | 
 | B | 
 | 6 | 
 | C | 
 | 3 | 
 | E | 
 | 9 | 
 | F | 
 | 4 | 
 | D | 
 | 5 | 
 | G | 
 | 5 | 
 | H | 
 | 8 | 

## Slide 93
EXAMPLE 2
A
B
E
H
 | A | 
 | 3 | 
 | B | 
 | 6 | 
 | C | 
 | 3 | 
 | E | 
 | 9 | 
 | F | 
 | 4 | 
 | D | 
 | 5 | 
 | G | 
 | 5 | 
 | H | 
 | 8 | 

## Slide 94
EXAMPLE 2
A
B
E
H
 | A | 
 | 3 | 
 | B | 
 | 6 | 
 | C | 
 | 3 | 
 | E | 
 | 8 | 
 | F | 
 | 4 | 
 | D | 
 | 5 | 
 | G | 
 | 5 | 
 | H | 
 | 8 | 

## Slide 95
EXAMPLE 2
A
B
E
H
 | A | 
 | 3 | 
 | B | 
 | 6 | 
 | C | 
 | 3 | 
 | E | 
 | 8 | 
 | F | 
 | 4 | 
 | D | 
 | 5 | 
 | G | 
 | 5 | 
 | H | 
 | 8 | 
A-B-F-H = 21
A-C-E-H = 21
A-D-E-H = 24
A-D-E-H = 21

## Slide 96
EXAMPLE 2
A
B
E
H
 | A | 
 | 3 | 
 | B | 
 | 6 | 
 | C | 
 | 3 | 
 | E | 
 | 6 | 
 | F | 
 | 4 | 
 | D | 
 | 5 | 
 | G | 
 | 5 | 
 | H | 
 | 8 | 
A-B-F-H = 21
A-C-E-H = 21
A-D-E-H = 22
A-D-E-H = 21

## Slide 97
EXAMPLE 2
A
B
E
H
 | A | 
 | 3 | 
 | B | 
 | 6 | 
 | C | 
 | 3 | 
 | E | 
 | 6 | 
 | F | 
 | 4 | 
 | D | 
 | 5 | 
 | G | 
 | 5 | 
 | H | 
 | 8 | 

## Slide 98
EXAMPLE 2
A
B
E
H
 | A | 
 | 3 | 
 | B | 
 | 6 | 
 | C | 
 | 3 | 
 | E | 
 | 6 | 
 | F | 
 | 4 | 
 | D | 
 | 5 | 
 | G | 
 | 5 | 
 | H | 
 | 5 | 

## Slide 99
EXAMPLE 2
A
B
E
H
 | A | 
 | 3 | 
 | B | 
 | 6 | 
 | C | 
 | 3 | 
 | E | 
 | 6 | 
 | F | 
 | 4 | 
 | D | 
 | 5 | 
 | G | 
 | 5 | 
 | H | 
 | 5 | 
A-B-F-H = 18
A-C-E-H = 17
A-D-E-H = 19
A-D-E-H = 18

## Slide 100
EXAMPLE 2
Critical path activities we can crash | Project duration | Project cost
 | 27 days | $22,450
A (2 days @ $250/day) | 26 days 25 days | $22,700 $22,950
E (3 days @ $1,750/day) | 24 days 23 days 22 days | $24,700 $26,450 $28,200
H (3 days @ $2,000/day) | 21 days 20 days 19 days | $30,200 $32,200 $24,200
Recall:
normal cost = $22,450
normal time = 27 days

## Slide 101
EXAMPLE 2
Critical path activities we can crash | Project duration | Project cost
 | 27 days | $22,450
A (2 days @ $250/day) | 26 days 25 days | $22,700 $22,950
E (3 days @ $1,750/day) | 24 days 23 days 22 days | $24,700 $26,450 $28,200
H (3 days @ $2,000/day) | 21 days 20 days 19 days | $30,200 $32,200 $24,200
Recall:
normal cost = $22,450
normal time = 27 days

## Slide 102
EXAMPLE 2
Critical path activities we can crash | Project duration | Project cost
 | 27 days | $22,450
A (2 days @ $250/day) | 26 days 25 days | $22,700 $22,950
E (3 days @ $1,750/day) | 24 days 23 days 22 days | $24,700 $26,450 $28,200
H (3 days @ $2,000/day) | 21 days 20 days 19 days | $30,200 $32,200 $24,200
Recall:
normal cost = $22,450
normal time = 27 days
A x 1 day

## Slide 103
EXAMPLE 2
Critical path activities we can crash | Project duration | Project cost
 | 27 days | $22,450
A (2 days @ $250/day) | 26 days 25 days | $22,700 $22,950
E (3 days @ $1,750/day) | 24 days 23 days 22 days | $24,700 $26,450 $28,200
H (3 days @ $2,000/day) | 21 days 20 days 19 days | $30,200 $32,200 $24,200
Recall:
normal cost = $22,450
normal time = 27 days
A x 1 day
A x 1 day
E x 1 day
E x 1 day

## Slide 104
EXAMPLE 3
 | Normal |  | Crashed |  | 
Activity | Cost | Duration | Extra Cost | Duration | Crash Cost
A | $2,000 | 10 days | $2,000 | 7 days | $667/day
B | $1,500 | 5 days | $3,000 | 3 days | $1,500/day
C | $3,000 | 12 days | $1,500 | 9 days | $500/day
D | $5,000 | 20 days | $3,000 | 15 days | $600/day
E | $2,500 | 8 days | $2,500 | 6 days | $1,250/day
F | $3,000 | 14 days | $2,500 | 10 days | $625/day
G | $6,000 | 12 days | $5,000 | 10 days | $2,500/day
H | $9,000 | 15 days | $3,000 | 12 days | $1,000/day
The cost of crashing a project must always be considered against the time saved in expediting the activity’s schedule.
Assume the critical path is
A-C-D-H (57 days)

## Slide 105
EXAMPLE 3
 | Normal |  | Crashed |  | 
Activity | Cost | Duration | Extra Cost | Duration | Crash Cost
A | $2,000 | 10 days | $2,000 | 7 days | $667/day
B | $1,500 | 5 days | $3,000 | 3 days | $1,500/day
C | $3,000 | 12 days | $1,500 | 9 days | $500/day
D | $5,000 | 20 days | $3,000 | 15 days | $600/day
E | $2,500 | 8 days | $2,500 | 6 days | $1,250/day
F | $3,000 | 14 days | $2,500 | 10 days | $625/day
G | $6,000 | 12 days | $5,000 | 10 days | $2,500/day
H | $9,000 | 15 days | $3,000 | 12 days | $1,000/day
The cost of crashing a project must always be considered against the time saved in expediting the activity’s schedule.
Assume the critical path is
A-C-D-H (57 days)

## Slide 106
EXAMPLE 3
 | Normal |  | Crashed |  | 
Activity | Cost | Duration | Extra Cost | Duration | Crash Cost
A | $2,000 | 10 days | $2,000 | 7 days | $667/day
B | $1,500 | 5 days | $3,000 | 3 days | $1,500/day
C | $3,000 | 12 days | $1,500 | 9 days | $500/day
D | $5,000 | 20 days | $3,000 | 15 days | $600/day
E | $2,500 | 8 days | $2,500 | 6 days | $1,250/day
F | $3,000 | 14 days | $2,500 | 10 days | $625/day
G | $6,000 | 12 days | $5,000 | 10 days | $2,500/day
H | $9,000 | 15 days | $3,000 | 12 days | $1,000/day
The cost of crashing a project must always be considered against the time saved in expediting the activity’s schedule.
Assume the critical path is
A-C-D-H (57 days)

## Slide 107
EXAMPLE 3
 | Normal |  | Crashed |  | 
Activity | Cost | Duration | Extra Cost | Duration | Crash Cost
A | $2,000 | 10 days | $2,000 | 7 days | $667/day
B | $1,500 | 5 days | $3,000 | 3 days | $1,500/day
C | $3,000 | 12 days | $1,500 | 9 days | $500/day
D | $5,000 | 20 days | $3,000 | 15 days | $600/day
E | $2,500 | 8 days | $2,500 | 6 days | $1,250/day
F | $3,000 | 14 days | $2,500 | 10 days | $625/day
G | $6,000 | 12 days | $5,000 | 10 days | $2,500/day
H | $9,000 | 15 days | $3,000 | 12 days | $1,000/day
The cost of crashing a project must always be considered against the time saved in expediting the activity’s schedule.
Assume the critical path is
A-C-D-H (57 days)

## Slide 108
EXAMPLE 3
 | Normal |  | Crashed |  | 
Activity | Cost | Duration | Extra Cost | Duration | Crash Cost
A | $2,000 | 10 days | $2,000 | 7 days | $667/day
B | $1,500 | 5 days | $3,000 | 3 days | $1,500/day
C | $3,000 | 12 days | $1,500 | 9 days | $500/day
D | $5,000 | 20 days | $3,000 | 15 days | $600/day
E | $2,500 | 8 days | $2,500 | 6 days | $1,250/day
F | $3,000 | 14 days | $2,500 | 10 days | $625/day
G | $6,000 | 12 days | $5,000 | 10 days | $2,500/day
H | $9,000 | 15 days | $3,000 | 12 days | $1,000/day
The cost of crashing a project must always be considered against the time saved in expediting the activity’s schedule.
Assume the critical path is
A-C-D-H (57 days)

## Slide 109
EXAMPLE 3
 | Normal |  | Crashed |  | 
Activity | Cost | Duration | Extra Cost | Duration | Crash Cost
A | $2,000 | 10 days | $2,000 | 7 days | $667/day
B | $1,500 | 5 days | $3,000 | 3 days | $1,500/day
C | $3,000 | 12 days | $1,500 | 9 days | $500/day
D | $5,000 | 20 days | $3,000 | 15 days | $600/day
E | $2,500 | 8 days | $2,500 | 6 days | $1,250/day
F | $3,000 | 14 days | $2,500 | 10 days | $625/day
G | $6,000 | 12 days | $5,000 | 10 days | $2,500/day
H | $9,000 | 15 days | $3,000 | 12 days | $1,000/day
The cost of crashing a project must always be considered against the time saved in expediting the activity’s schedule.
Assume the critical path is
A-C-D-H (57 days)

## Slide 110
EXAMPLE 3
 | Normal |  | Crashed |  | 
Activity | Cost | Duration | Extra Cost | Duration | Crash Cost
A | $2,000 | 10 days | $2,000 | 7 days | $667/day
B | $1,500 | 5 days | $3,000 | 3 days | $1,500/day
C | $3,000 | 12 days | $1,500 | 9 days | $500/day
D | $5,000 | 20 days | $3,000 | 15 days | $600/day
E | $2,500 | 8 days | $2,500 | 6 days | $1,250/day
F | $3,000 | 14 days | $2,500 | 10 days | $625/day
G | $6,000 | 12 days | $5,000 | 10 days | $2,500/day
H | $9,000 | 15 days | $3,000 | 12 days | $1,000/day
The cost of crashing a project must always be considered against the time saved in expediting the activity’s schedule.
Assume the critical path is
A-C-D-H (57 days)

## Slide 111
EXAMPLE 3
 | Normal |  | Crashed |  | 
Activity | Cost | Duration | Extra Cost | Duration | Crash Cost
A | $2,000 | 10 days | $2,000 | 7 days | $667/day
B | $1,500 | 5 days | $3,000 | 3 days | $1,500/day
C | $3,000 | 12 days | $1,500 | 9 days | $500/day
D | $5,000 | 20 days | $3,000 | 15 days | $600/day
E | $2,500 | 8 days | $2,500 | 6 days | $1,250/day
F | $3,000 | 14 days | $2,500 | 10 days | $625/day
G | $6,000 | 12 days | $5,000 | 10 days | $2,500/day
H | $9,000 | 15 days | $3,000 | 12 days | $1,000/day
The cost of crashing a project must always be considered against the time saved in expediting the activity’s schedule.
Assume the critical path is
A-C-D-H (57 days)

## Slide 112
EXAMPLE 3
Balancing act:
At what point is it no longer economically viable to continue crashing activities?
Total normal project days = 57 days
Also suppose that the project team will be charged the following:
Overhead at $200/day fixed rate
A series of late penalties will kick in if the project is not completed in 50 days

## Slide 113
EXAMPLE 3
Project duration | Direct costs | Late penalties | Overhead costs | Total costs
57 days (normal) | $32,000 (normal) | $5,000 | $11,400 | $48,400
Total normal project days = 57 days
Also suppose that the project team will be charged the following:
Overhead at $200/day fixed rate
A series of late penalties will kick in if the project is not completed in 50 days

## Slide 114
EXAMPLE 3
Project duration | Direct costs | Late penalties | Overhead costs | Total costs
57 days (normal) | $32,000 (normal) | $5,000 | $11,400 | $48,400
Total normal project days = 57 days
Also suppose that the project team will be charged the following:
Overhead at $200/day fixed rate
A series of late penalties will kick in if the project is not completed in 50 days

## Slide 115
EXAMPLE 3
Project duration | Direct costs | Late penalties | Overhead costs | Total costs
57 days (normal) | $32,000 (normal) | $5,000 | $11,400 | $48,400
Total normal project days = 57 days
Also suppose that the project team will be charged the following:
Overhead at $200/day fixed rate
A series of late penalties will kick in if the project is not completed in 50 days

## Slide 116
EXAMPLE 3
Project duration | Direct costs | Late penalties | Overhead costs | Total costs
57 days (normal) | $32,000 (normal) | $5,000 | $11,400 | $48,400
54 days |  |  |  | 
51 days |  |  |  | 
48 days |  |  |  | 
Total normal project days = 57 days
Also suppose that the project team will be charged the following:
Overhead at $200/day fixed rate
A series of late penalties will kick in if the project is not completed in 50 days
Balancing act:
At what point is it no longer economically viable to continue crashing activities?

## Slide 117
EXAMPLE 3
Project duration | Direct costs | Late penalties | Overhead costs | Total costs
57 days (normal) | $32,000 (normal) | $5,000 | $11,400 | $48,400
54 days | $33,500 (crashed C) | $3,000 | $10,800 | $47,300
Total normal project days = 57 days
Also suppose that the project team will be charged the following:
Overhead at $200/day fixed rate
A series of late penalties will kick in if the project is not completed in 50 days

## Slide 118
EXAMPLE 3
Project duration | Direct costs | Late penalties | Overhead costs | Total costs
57 days (normal) | $32,000 (normal) | $5,000 | $11,400 | $48,400
54 days | $33,500 (crashed C) | $3,000 | $10,800 | $47,300
51 days | $35,500 (crashed A) | $1,000 | $10,200 | $46,700
Total normal project days = 57 days
Also suppose that the project team will be charged the following:
Overhead at $200/day fixed rate
A series of late penalties will kick in if the project is not completed in 50 days

## Slide 119
EXAMPLE 3
Project duration | Direct costs | Late penalties | Overhead costs | Total costs
57 days (normal) | $32,000 (normal) | $5,000 | $11,400 | $48,400
54 days | $33,500 (crashed C) | $3,000 | $10,800 | $47,300
51 days | $35,500 (crashed A) | $1,000 | $10,200 | $46,700
48 days | $38,500 (crashed H) | $0 | $9,600 | $48,100
Total normal project days = 57 days
Also suppose that the project team will be charged the following:
Overhead at $200/day fixed rate
A series of late penalties will kick in if the project is not completed in 50 days

## Slide 120
Project Scheduling:
Gantt Charts

## Slide 121
GANTT CHARTS
Establish a time-phased network
Can be used as a tracking tool
Benefits of Gantt charts
Easy to comprehend
Identify the schedule baseline network
Allow for updating and control
Identify resource needs
Easy to create

## Slide 122
GANTT CHARTS

## Slide 123
GANTT CHARTS

## Slide 124
GANTT CHARTS

## Slide 125
GANTT CHARTS

## Slide 126
GANTT CHARTS

## Slide 127
GANTT CHARTS

## Slide 128
GANTT CHARTS

## Slide 129
GANTT CHARTS

## Slide 130
EXAMPLE
Activity | Pred. | Duration
A | None | 5
B | A | 5
C | A | 6
D | B, C | 13
E | B | 6
F | D | 4
G | C | 9
H | E, F, G | 2

## Slide 131
EXAMPLE
Activity | Pred. | Duration
A | None | 5
B | A | 5
C | A | 6
D | B, C | 13
E | B | 6
F | D | 4
G | C | 9
H | E, F, G | 2

## Slide 132
EXAMPLE
Activity | Pred. | Duration
A | None | 5
B | A | 5
C | A | 6
D | B, C | 13
E | B | 6
F | D | 4
G | C | 9
H | E, F, G | 2

## Slide 133
EXAMPLE
Activity | Pred. | Duration
A | None | 5
B | A | 5
C | A | 6
D | B, C | 13
E | B | 6
F | D | 4
G | C | 9
H | E, F, G | 2

## Slide 134
EXAMPLE
Activity | Pred. | Duration
A | None | 5
B | A | 5
C | A | 6
D | B, C | 13
E | B | 6
F | D | 4
G | C | 9
H | E, F, G | 2

## Slide 135
EXAMPLE
Activity | Pred. | Duration
A | None | 5
B | A | 5
C | A | 6
D | B, C | 13
E | B | 6
F | D | 4
G | C | 9
H | E, F, G | 2

## Slide 136
EXAMPLE
A |  |  |  |  |  | 
B |  |  |  |  |  | 
C |  |  |  |  |  | 
D |  |  |  |  |  | 
E |  |  |  |  |  | 
F |  |  |  |  |  | 
G |  |  |  |  |  | 
H |  |  |  |  |  | 
0
5
10
15
20
25
30

## Slide 137
EXAMPLE
A |  |  |  |  |  | 
B |  |  |  |  |  | 
C |  |  |  |  |  | 
D |  |  |  |  |  | 
E |  |  |  |  |  | 
F |  |  |  |  |  | 
G |  |  |  |  |  | 
H |  |  |  |  |  | 
0
5
10
15
20
25
30

## Slide 138
EXAMPLE
A |  |  |  |  |  | 
B |  |  |  |  |  | 
C |  |  |  |  |  | 
D |  |  |  |  |  | 
E |  |  |  |  |  | 
F |  |  |  |  |  | 
G |  |  |  |  |  | 
H |  |  |  |  |  | 
0
5
10
15
20
25
30

## Slide 139
EXAMPLE
A |  |  |  |  |  | 
B |  |  |  |  |  | 
C |  |  |  |  |  | 
D |  |  |  |  |  | 
E |  |  |  |  |  | 
F |  |  |  |  |  | 
G |  |  |  |  |  | 
H |  |  |  |  |  | 
0
5
10
15
20
25
30

## Slide 140
EXAMPLE
A |  |  |  |  |  | 
B |  |  |  |  |  | 
C |  |  |  |  |  | 
D |  |  |  |  |  | 
E |  |  |  |  |  | 
F |  |  |  |  |  | 
G |  |  |  |  |  | 
H |  |  |  |  |  | 
0
5
10
15
20
25
30

## Slide 141
EXAMPLE
A |  |  |  |  |  | 
B |  |  |  |  |  | 
C |  |  |  |  |  | 
D |  |  |  |  |  | 
E |  |  |  |  |  | 
F |  |  |  |  |  | 
G |  |  |  |  |  | 
H |  |  |  |  |  | 
0
5
10
15
20
25
30

## Slide 142
EXAMPLE
A |  |  |  |  |  | 
B |  |  |  |  |  | 
C |  |  |  |  |  | 
D |  |  |  |  |  | 
E |  |  |  |  |  | 
F |  |  |  |  |  | 
G |  |  |  |  |  | 
H |  |  |  |  |  | 
0
5
10
15
20
25
30

## Slide 143
EXAMPLE
A |  |  |  |  |  | 
B |  |  |  |  |  | 
C |  |  |  |  |  | 
D |  |  |  |  |  | 
E |  |  |  |  |  | 
F |  |  |  |  |  | 
G |  |  |  |  |  | 
H |  |  |  |  |  | 
0
5
10
15
20
25
30

## Slide 144
EXAMPLE
A |  |  |  |  |  | 
B |  |  |  |  |  | 
C |  |  |  |  |  | 
D |  |  |  |  |  | 
E |  |  |  |  |  | 
F |  |  |  |  |  | 
G |  |  |  |  |  | 
H |  |  |  |  |  | 
0
5
10
15
20
25
30

## Slide 145
EXAMPLE
A |  |  |  |  |  | 
B |  |  |  |  |  | 
C |  |  |  |  |  | 
D |  |  |  |  |  | 
E |  |  |  |  |  | 
F |  |  |  |  |  | 
G |  |  |  |  |  | 
H |  |  |  |  |  | 
0
5
10
15
20
25
30

## Slide 146
EXAMPLE
A |  |  |  |  |  | 
B |  |  |  |  |  | 
C |  |  |  |  |  | 
D |  |  |  |  |  | 
E |  |  |  |  |  | 
F |  |  |  |  |  | 
G |  |  |  |  |  | 
H |  |  |  |  |  | 
0
5
10
15
20
25
30

## Slide 147
EXAMPLE
A |  |  |  |  |  | 
B |  |  |  |  |  | 
C |  |  |  |  |  | 
D |  |  |  |  |  | 
E |  |  |  |  |  | 
F |  |  |  |  |  | 
G |  |  |  |  |  | 
H |  |  |  |  |  | 
0
5
10
15
20
25
30

## Slide 148
EXAMPLE
A |  |  |  |  |  | 
B |  |  |  |  |  | 
C |  |  |  |  |  | 
D |  |  |  |  |  | 
E |  |  |  |  |  | 
F |  |  |  |  |  | 
G |  |  |  |  |  | 
H |  |  |  |  |  | 
0
5
10
15
20
25
30

## Slide 149
EXAMPLE
A |  |  |  |  |  | 
B |  |  |  |  |  | 
C |  |  |  |  |  | 
D |  |  |  |  |  | 
E |  |  |  |  |  | 
F |  |  |  |  |  | 
G |  |  |  |  |  | 
H |  |  |  |  |  | 
0
5
10
15
20
25
30

## Slide 150
EXAMPLE
A |  |  |  |  |  | 
B |  |  |  |  |  | 
C |  |  |  |  |  | 
D |  |  |  |  |  | 
E |  |  |  |  |  | 
F |  |  |  |  |  | 
G |  |  |  |  |  | 
H |  |  |  |  |  | 
0
5
10
15
20
25
30

## Slide 151
EXAMPLE
A |  |  |  |  |  | 
B |  |  |  |  |  | 
C |  |  |  |  |  | 
D |  |  |  |  |  | 
E |  |  |  |  |  | 
F |  |  |  |  |  | 
G |  |  |  |  |  | 
H |  |  |  |  |  | 
0
5
10
15
20
25
30

## Slide 152
EXAMPLE
A |  |  |  |  |  | 
B |  |  |  |  |  | 
C |  |  |  |  |  | 
D |  |  |  |  |  | 
E |  |  |  |  |  | 
F |  |  |  |  |  | 
G |  |  |  |  |  | 
H |  |  |  |  |  | 
0
5
10
15
20
25
30

## Slide 153
EXAMPLE
A |  |  |  |  |  | 
B |  |  |  |  |  | 
C |  |  |  |  |  | 
D |  |  |  |  |  | 
E |  |  |  |  |  | 
F |  |  |  |  |  | 
G |  |  |  |  |  | 
H |  |  |  |  |  | 
0
5
10
15
20
25
30

## Slide 154
EXAMPLE
A |  |  |  |  |  | 
B |  |  |  |  |  | 
C |  |  |  |  |  | 
D |  |  |  |  |  | 
E |  |  |  |  |  | 
F |  |  |  |  |  | 
G |  |  |  |  |  | 
H |  |  |  |  |  | 
0
5
10
15
20
25
30

## Slide 155
Project Monitoring, Control, & Evaluation

## Slide 156
MONITORING AND CONTROL
One of the most significant challenges of running a project – maintaining accurate monitoring and control systems for its implementation
Project monitoring and control are principal mechanisms to helps the project team stay on top of the project’s evolving status
“No news is good news” is not good enough – we need to clearly understand the benefits that can be derived from careful and thorough status assessments as the project progresses

## Slide 157
MONITORING AND CONTROL
We need to know what information should be measured and when the best time to measure it is
We want the information as soon as we can get it and we want it to be as up-to-date as possible
Systematic project control is comprehensive, accurate, & timely

## Slide 158
MONITORING AND CONTROL
Data collected are determined by which metrics will be used for project control
Typical key data include actual activity duration, resource usage and rates, actual costs - compare against planned times, resources, budgets
A major portion of monitoring focuses on cost/schedule concerns – provide the PM and stakeholders with data to answer:
  What is the current status in terms of schedule and cost?
  When will the project be completed & how much will it cost?
  What, who, where are the causes for overruns?
  What did we get for the amount we spent?
  If there are overruns mid-way can we adjust our forecast?

## Slide 159
PROJECT CONTROL CYCLES
General model of organizational control – four components that operate in a continuous cycle
Setting a goal
Measuring progress
Comparing actual With planned performance
Taking action
Control is the process of comparing actual performance against planned performance, to identify deviations, evaluate possible alternative courses of action, and take appropriate corrective action

## Slide 160
PROJECT CONTROL CYCLES
1. Setting a goal
Setting the project plan / creating a WBS to establish all the deliverables & work packages that are associated with the project
2. Measuring progress
Need a system in place that will allow project managers to gather information as quickly as possible – need to clearly define what to measure

## Slide 161
PROJECT CONTROL CYCLES
3. Comparing actual with planned performance
Perform a gap analysis to determine the goals and the degree to which the actual performance lives up to those goals
4. Taking action
Once deviations are detected, we need to take corrective action (can be significant or minor), and then the cycle begins again

## Slide 162
MONITORING PROJECT PERFORMANCE
Once we have established a project baseline budget, one of the most important methods for indicating the ongoing status of the project is to evaluate it against the original budget projections.
A major goal of progress reporting is to catch any negative variances from the original plan as early as possible to determine if any corrective action is required.

## Slide 163
S-CURVE
Individual task budgets & overall project budget are important
A project S-curve represents the typical form of the relationship between the money expended and the time (time/cost analysis)
The S-curve represents the project’s baseline budget against which actual budget expenditures can be evaluated
Copyright © 2016 Pearson Education, Ltd.

## Slide 164
S-CURVE
Copyright © 2016 Pearson Education, Ltd.

## Slide 165
S-CURVE EXAMPLE
Four work packages = Design, Engineer, Install, Test
Project budget = $80,000
Project duration = 45 weeks

## Slide 166
S-CURVE EXAMPLE
Four work packages = Design, Engineer, Install, Test
Project budget = $80,000
Project duration = 45 weeks

## Slide 167
S-CURVE EXAMPLE
Four work packages = Design, Engineer, Install, Test
Project budget = $80,000
Project duration = 45 weeks

## Slide 168
S-CURVE EXAMPLE
Four work packages = Design, Engineer, Install, Test
Project budget = $80,000
Project duration = 45 weeks

## Slide 169
S-CURVE EXAMPLE

## Slide 170
S-CURVE EXAMPLE
Suppose we want to check at week 21 how we are progressing with respect to our budget.

## Slide 171
S-CURVE EXAMPLE
Suppose when we check at week 21 and find our actual project expenditure is cumulatively only $40,000 (supposed to be $50,000)

## Slide 172
S-CURVE EXAMPLE
Suppose when we check at week 21 and find our actual project expenditure is cumulatively only $40,000 (supposed to be $50,000)
Quick visual for linking project costs (budgeted and actual) over the project’s schedule

## Slide 173
S-CURVE EXAMPLE
Suppose when we check at week 21 and find our actual project expenditure is cumulatively only $40,000 (supposed to be $50,000)
Quick visual for linking project costs (budgeted and actual) over the project’s schedule
Does not allow us to make reasonable interpretations for the cause of the variance

## Slide 174
S-CURVE EXAMPLE
Suppose when we check at week 21 and find our actual project expenditure is cumulatively only $40,000 (supposed to be $50,000)
Quick visual for linking project costs (budgeted and actual) over the project’s schedule
Does not allow us to make reasonable interpretations for the cause of the variance
Reactive data – we are plotting after the money has already been spent

## Slide 175
MILESTONE ANALYSIS
Milestones are events or stages of the project that represent a significant accomplishment.
Completion of a deliverable (a combination of multiple tasks)
Important activity on the critical path
Calendar dates
Any ‘road marker’ along the project’s life cycle
Notes: .

## Slide 176
MILESTONE ANALYSIS
Milestones:
Signal completion of important steps
Motivate team and suppliers
Offer reevaluation points
Help coordinate schedules
Identify key review gates
Signal other team members when their participation begins
Delineate work packages

## Slide 177
TRACKING GANTT CHART
Quite easy to understand
Visual nature of report is easy to assimilate and interpret
Sense of real-time project control
Not identifying the underlying source of problems
The reason for the slippage cannot be inferred from the data presented
Difficult to accurately estimate time to completion from a baseline schedule
Should be used in conjunction with other techniques

## Slide 178
TRACKING GANTT CHART
Copyright © 2018 McGraw-Hill Education

## Slide 179
EARNED VALUE MANAGEMENT
179
S-Curves
Time
Cost

## Slide 180
EARNED VALUE MANAGEMENT
180
S-Curves
Milestones/Tracking Gantt
Time
Cost
Scope (Performance)

## Slide 181
EARNED VALUE MANAGEMENT
181
S-Curves
Milestones/Tracking Gantt
Time
Cost
Scope (Performance)

## Slide 182
EARNED VALUE MANAGEMENT
182
S-Curves
Milestones/Tracking Gantt
Time
Cost
Scope (Performance)
Earned Value Management

## Slide 183
EARNED VALUE MANAGEMENT
Earned Value Management (EVM) recognizes that it is necessary to jointly consider the impact of time, cost, and project performance on any analysis of current project status
Earned Value (EV) directly links all three primary project success metrics (cost, schedule, and performance).

## Slide 184
EARNED VALUE MANAGEMENT
Copyright © 2016 Pearson Education, Ltd.

## Slide 185
EARNED VALUE MANAGEMENT
Copyright © 2016 Pearson Education, Ltd.

## Slide 186
EARNED VALUE MANAGEMENT
Copyright © 2016 Pearson Education, Ltd.

## Slide 187
EARNED VALUE MANAGEMENT
Copyright © 2016 Pearson Education, Ltd.

## Slide 188
EARNED VALUE MANAGEMENT
Copyright © 2016 Pearson Education, Ltd.

## Slide 189
EARNED VALUE MANAGEMENT
Copyright © 2016 Pearson Education, Ltd.

## Slide 190
EVM EXAMPLE
Four work packages = Design, Engineer, Install, Test
Project budget = $80,000
Project duration = 45 weeks

## Slide 191
EVM EXAMPLE
Four work packages = Design, Engineer, Install, Test
Project budget = $80,000
Project duration = 45 weeks
We know the baseline for how our project should perform, and now we can assess how we are actually doing. Assume we want to check how we are doing at week 30.

## Slide 192
EVM EXAMPLE
Four work packages = Design, Engineer, Install, Test
Project budget = $80,000
Project duration = 45 weeks
We know the baseline for how our project should perform, and now we can assess how we are actually doing. Assume we want to check how we are doing at week 30.

## Slide 193
EVM EXAMPLE
Four work packages = Design, Engineer, Install, Test
Project budget = $80,000
Project duration = 45 weeks
We know the baseline for how our project should perform, and now we can assess how we are actually doing. Assume we want to check how we are doing at week 30.

## Slide 194
EVM EXAMPLE
.
What is the status of this project in terms of budget, schedule, and performance? Focus exclusively on the relevant information for determining earned value as of week 30.
Planned budget is multiplied by the percentage completed in order to determine the earned value to date for the work packages.

## Slide 195
EVM EXAMPLE
.
What is the status of this project in terms of budget, schedule, and performance? Focus exclusively on the relevant information for determining earned value as of week 30.
Planned budget is multiplied by the percentage completed in order to determine the earned value to date for the work packages.

## Slide 196
EVM EXAMPLE
.
What is the status of this project in terms of budget, schedule, and performance? Focus exclusively on the relevant information for determining earned value as of week 30.
Planned budget is multiplied by the percentage completed in order to determine the earned value to date for the work packages.

## Slide 197
EVM EXAMPLE
.
What is the status of this project in terms of budget, schedule, and performance? Focus exclusively on the relevant information for determining earned value as of week 30.
Planned budget is multiplied by the percentage completed in order to determine the earned value to date for the work packages.

## Slide 198
$8,000 x 100% = $8,000
$28,000 x 100% = $28,000
$30,000 x 50% = $15,000
Cumulative earned value = $51,000
EVM EXAMPLE
.
What is the status of this project in terms of budget, schedule, and performance? Focus exclusively on the relevant information for determining earned value as of week 30.
Planned budget is multiplied by the percentage completed in order to determine the earned value to date for the work packages.

## Slide 199
What is the status of this project in terms of budget, schedule, and performance?